## Sheet1
Performance in Initiating Q1 2018-19
Submission Details
Status | Accepted
Open Date | 2018-07-01
Deadline Date | 2018-07-30
Date Submitted | 2018-07-17
Type | Performance in Initiating
NHS provider | The Robert Jones and Agnes Hunt Orthopaedic Hospital NHS Foundation Trust
Showing records 1 to 3 of 3.
Pages: 1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
122905 | 16/SW/0154 | 204891 | Evaluation of a care pathway for patients with long-term pain after knee replacement | Yes | 2018-01-12 | 82 | 66 | 148 | 2017-07-05 | 2017-08-17 | 2016-08-04 | 2017-08-17 | 2017-11-07 | Please Select... | 2017-11-15 | A - Permissions delayed/denied | Delay at site due to misunderstanding by Clinical Lead for area preventing the study to go ahead. This was resolved and study now active. | NHS Provider
122906 | 17/SC/0139 | 197936 | SPAARK: Study of Peri-Articular Anaesthetic for Replacement of the Knee | Yes | 2018-04-12 | 147 | 57 | 204 | 2017-09-20 | 2017-09-20 | 2017-09-18 | 2017-09-20 | 2018-02-14 | Please Select... | 2018-03-01 | D - Sponsor Delays | Delay was due to Sponsor submitting a substantial amendment to address the control drug and to have sufficient supplies in the UK of the study and control drug for the study. | Sponsor
122907 | 16/SC/0188 | 198227 | Osteoarthritis Thumb Therapy trial. A randomised controlled trial into the effectiveness and efficacy of splints in thumb base osteoarthritis. | Yes | 2018-02-28 | 83 | 44 | 127 | 2017-10-24 | 2017-10-24 | 2016-06-20 | 2017-10-24 | 2018-01-15 | Please Select... | 2018-01-15 | E - Staff availability issues; J - Other | Delay due to time taken to arrange SIV and capacity within the Research dept. to assist with the running of the study including set-up. Christmas holidays also played a role i.e. unavailability of staff. | Both