## DataSheet
Id | TrustId | SubmissionId | MetaSubmissionId | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | AddedByUserId | AmendedByUserId | DateAdded | DateAmended | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | K - Not Used | L - Not Used | M - Not Used | N - Not Used | O - Not Used | Comments | Reasons for delay correspond to: | Errors
60173 | 1066 | 2451 | 31 | 12/NE/0293 | Prospective single arm multiconfiguration investigation to assess the functional performance of Attune primary total knee arthroplasty system. (10004 PRO Knee Assessment- Attune). | 2014-05-28 | 2014-07-02 | Yes | 2014-07-09 | 35 | 7 | 42 | Yes | Unknown | Unknown | 2014-10-22 | 2015-07-29 | [16 empty] | Please Select...
60174 | 1066 | 2451 | 31 | 14/SW/0072 | Understanding treatment of infection after joint replacement: a qualitative study (INFORM) | 2014-07-02 | 2014-07-02 | Yes | 2014-09-24 | 0 | 84 | 84 | No | Unknown | Unknown | 2014-10-22 | 42214 |  |  |  | Y |  | Y | [9 empty] | Delayed to 05/08/2014 in receiving the "green light" from the Sponsor, followed by delay in finding suitable patients. | Both
60175 | 1066 | 2451 | 31 | 12/SC/0028 | Can Shoulder Arthroscopy Work- CSAW | 2014-07-10 | 2014-07-21 | Yes | 2014-10-14 | 11 | 85 | 96 | No | CTP Submission Platform | Unknown | 2014-10-22 | 42214 | [5 empty] | Y | [9 empty] | Delay due to type of patient required for study | Neither
60176 | 1066 | 2451 | 31 | 14/EM/1027 | Early v protected weight bearing post microfracture surgery | 2014-08-17 | 2014-09-08 | Yes | 2015-02-09 | 22 | 154 | 176 | No | CTP Submission Platform | Unknown | 2014-10-22 | 42214 | [9 empty] | Y | [5 empty] | Delay due to amendment required to the protocol to enhance recruitment | NHS Provider
60177 | 1066 | 2451 | 31 | 13/NW/0663 | A Questionnaire for the Chronic Spinal Cord Injury Patient Population: 'Translational Research for Spinal Cord Injury (SCI): Current and Future Perspectives'. | 2014-07-31 | 2014-09-17 | Yes | 2014-09-23 | 48 | 6 | 54 | Yes | CTP Submission Platform | Unknown | 2014-10-22 | 42214 | [15 empty] | Potential participants have been approached, but no participant conseted to date. | Neither
60178 | 1066 | 2451 | 31 | 14/LO/0775 | An open non-comparitive clinical investigation of a novel decellularised porcine xenograft (dCell meniscus) for partial replacement of the meniscus. | 2014-09-23 | 2014-10-01 | No |  | 8 |  |  |  | CTP Submission Platform | Unknown | 2015-01-16 | 42214 |  |  |  | Y | [5 empty] | Y | [5 empty] | Delay with Sponsor being able to supply surgery instruments. Delay also due to Imaging Dept. capacity to prvide MRI scans for research v managing waiting times. | Both
60179 | 1066 | 2451 | 31 | 14/SC/1101 | Efficacy of a probiotic preparation (Yakult) containing a minimum of 6.5 x 10 to the power 9 Lactobacillus casei Shirota (LcS) compared to placebo for the prevention of AAD. | 2014-08-13 | 2014-10-22 | Yes | 2014-11-14 | 70 | 23 | 93 | No | CTP Submission Platform | Unknown | 2015-01-16 | 42214 |  |  |  | Y |  |  |  | Y | [7 empty] | Delay with Lead NHS site acting as Sponsor providing contract and written confirmation of funding. | Sponsor
60180 | 1066 | 2451 | 31 | 13/NW/0189 | Global prospective multicentre non-randomised controlled non-inferiortrial to evaluate symptom relief in patients with medical knee OA treated with the KineSpring implant for load reduction comapared to High tibial osteotomy (HTO). | 2014-09-23 | 2014-10-24 | Yes | 2014-11-19 | 31 | 26 | 57 | Yes | CTP Submission Platform | Unknown | 2015-01-16 | 42214 | [16 empty] | Please Select...
60181 | 1066 | 2451 | 31 | 13/SC/0418 | An exploration of strategies to enhance physical activity (PA) in people with Rheumatoid Arthritis (RA) | 2014-11-04 | 2014-11-12 | Yes | 2015-01-06 | 8 | 55 | 63 | Yes | CTP Submission Platform | Unknown | 2015-01-16 | 42214 | [16 empty] | Please Select...
60182 | 1066 | 2451 | 31 | 14/NW/0217 | What is the best way to fuse lumbar spine - anterior or posterior? | 2014-08-06 | 2014-12-01 | No |  | 117 |  |  |  | Unknown | Unknown | 2015-01-16 | 42214 | [9 empty] | Y | [5 empty] | Delay in securing agreement with Support Service Dept. - Imaging for MRI, issue being waiting time targets v research. | NHS Provider
60183 | 1066 | 2451 | 31 | 14/SC/1199 | Investigation of bone mineral content and body composition in men with coeliac disease | 2014-11-10 | 2014-11-17 | Yes | 2014-12-09 | 7 | 22 | 29 | Yes | CTP Submission Platform | Unknown | 2015-01-26 | 42214 | [16 empty] | Please Select...
60184 | 1066 | 2451 | 31 | 05/Q0508/95 | CHARMS (Childhood arthritis response to medication study) | 2015-01-05 | 2015-01-06 | No |  | 1 |  |  |  | CTP Submission Platform | Unknown | 2015-04-27 | 42214 | [5 empty] | Y | [10 empty] | Neither
60185 | 1066 | 2451 | 31 | 14/WM/0124 | UK full randomised controlled trial of arthroscopic surgery for hip impingement versus best conventional care (UK FASHIoN) | 2015-01-06 | 2015-01-07 | Yes | 2015-02-11 | 1 | 35 | 36 | Yes | CTP Submission Platform | Unknown | 2015-04-27 | 42214 | [16 empty] | Please Select...
60186 | 1066 | 2451 | 31 | 12/NW/0361 | A pragmatic randomised controlled trial comparing the effectiveness and cost effectiveness of levetiracetam and zonisamide versus standard treatments for epilepsy: A comparison of Standard and Antiepileptic Drugs (SANADII) | 2015-02-02 | 2015-02-04 | No |  | 2 |  |  |  | Unknown | Unknown | 2015-04-28 | 42214 | [5 empty] | Y |  |  | Y | [6 empty] | Rare patients at this Trust | Neither
60187 | 1066 | 2451 | 31 | 14/SW/1166 | A multi-centered randomised trial to compare 1-stage with 2-stage revision surgery for prosthetic hip joint infection. | 2015-01-18 | 2015-02-18 | No |  | 31 |  |  |  | Unknown | Unknown | 2015-04-28 | 42214 | [5 empty] | Y | [9 empty] | No Revision patients seen to date | Neither
60188 | 1066 | 2451 | 31 | 14/WM/1063 | Platelet-rich plasma (PRP) versus Autologous blood versus placebo in the treatment of resistant tennis elbow | 2015-02-23 | 2015-02-24 | No |  | 1 |  |  |  | Unknown | Unknown | 2015-04-28 | 42214 | [5 empty] | Y |  |  |  | Y | [5 empty] | 1 patient consented, but not randomised yet - awaiting clinic date. | NHS Provider
60189 | 1066 | 2451 | 31 | 15/NW/0005 | Medial Rotation Knee Randomised Controlled Trial All-polyethylene versus metal backed tibia | 2015-03-02 | 2015-03-09 | No |  | 7 |  |  |  | Unknown | Unknown | 2015-04-28 | 42214 | [5 empty] | Y | [10 empty] | Neither
60190 | 1066 | 2451 | 31 | n/a | Survey of Physiotherapist INtervention with PMR patients | 2015-03-04 | 2015-03-09 | No |  | 5 |  |  |  | Unknown | Unknown | 2015-04-28 | 42214 | [9 empty] | Y | [5 empty] | This is a physiotherapist survey - no patient involvement. | Neither
60191 | 1066 | 2451 | 31 | 08/HO604/170 | A multicentre randomised double blind placebo controlled efficacy and safety trial if i.v. zolendronic acid twice yearly compared to placebo in osteoporotic children treated with glucocorticoids. | 2015-03-16 | 2015-03-18 | No |  | 2 |  |  |  | Unknown | Unknown | 2015-04-28 | 42214 | [9 empty] | Y | [5 empty] | Await SIV. Study to close at this site band site to become a PIC and send eligible patient to another research site. | Sponsor
60192 | 1066 | 2451 | 31 | 14/NW/0339 | POPULAR | 2015-02-24 | 2015-02-26 | Yes | 2015-03-04 | 2 | 6 | 8 | Yes | Unknown | Unknown | 2015-04-30 | 42214 | [16 empty] | Please Select...
60193 | 1066 | 2451 | 31 | 15/NW/0005 | Medial Rotation Knee Randomised Controlled Trial All-polyethylene versus metal backed tibia | 2015-03-02 | 2015-03-09 | Yes | 2015-04-14 | 7 | 36 | 43 | Yes | Unknown | Unknown | 2015-07-29 | 42214 | [16 empty] | Please Select...
60194 | 1066 | 2451 | 31 | 14/EE/0204 | Hydrotherapy for DMD: a pilot feasibility randomised controlled trial in children | 2015-04-14 | 2015-04-28 | Yes | 2015-06-24 | 14 | 57 | 71 | No | Unknown | Unknown | 2015-07-29 | 42214 | [5 empty] | Y |  |  | Y | [6 empty] | Small number of eligible patients. | Neither
60195 | 1066 | 2451 | 31 | 15/WM/0078 | The SCOPIC trial – Sciatica outcomes in primary care. Stratified care for patients with sciatica and suspected sciatica in primary care | 2015-06-26 | 2015-06-26 | Yes | 2015-07-06 | 0 | 10 | 10 | Yes | Unknown | Unknown | 2015-07-29 | 42214 | [16 empty] | Please Select...
Upload Submission
Validate

## Hidden Data (hidden)
SpreadsheetOne - Hidden Data
******** PLEASE DO NOT CHANGE ANY OF THESE VALUES ********
| Hidden Data Key | Hidden Data Value |  | XML |  | Class
| Is First Open | FALSE |  | <?xml version="1.0" encoding="utf-16"?> <DataTableDataExportContainerOfPerformanceInitiationDetail xmlns:xsd="http://www.w3.org/2001/XMLSchema" xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance"> <DataTypeName>Exbos.Applications.NHSRBVP.Components.BusinessObjects.PerformanceInitiationDetail, Exbos.Applications.NHSRBVP.Components.BusinessObjects, Version=1.0.10.0, Culture=neutral, PublicKeyToken=null</DataTypeName> <Site Id="1" AddressId="-1" StatusId="51" TypeId="401" CultureId="1" AddedByUserId="1" AmendedByUserId="1" DateAdded="2013-06-15T22:56:16" DateAmended="2013-06-15T22:56:16"> <Name>CTP Submission Platform</Name> <Description/> </Site> </DataTableDataExportContainerOfPerformanceInitiationDetail> |  | PerformanceInitiationDetail
| Development Mode | FALSE
| Data Id | 2451
| User Id | -1
| Data Id | 40
<ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>1</Order> <Name>Id</Name> <FriendlyName>Id</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>2</Order> <Name>TrustId</Name> <FriendlyName>TrustId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">1066</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>3</Order> <Name>SubmissionId</Name> <FriendlyName>SubmissionId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2451</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>4</Order> <Name>MetaSubmissionId</Name> <FriendlyName>MetaSubmissionId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">31</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>NotEmpty</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>5</Order> <Name>ReferenceNumber</Name> <FriendlyName>Research Ethics Committee Reference Number</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>NotEmpty</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>6</Order> <Name>TrialName</Name> <FriendlyName>Name of Trial</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>7</Order> <Name>ReceiptDate</Name> <FriendlyName>Date of Receipt of Valid Research Application</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>true</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>8</Order> <Name>PermissionDate</Name> <FriendlyName>Date of NHS Permission</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>9</Order> <Name>FirstPatientRecruitedTypeId</Name> <FriendlyName>First Patient Recruited?</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>1400</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>1401</int> </key> <value> <string>Yes</string> </value> </item> <item> <key> <int>1402</int> </key> <value> <string>Yes - Date Unavailable</string> </value> </item> <item> <key> <int>1403</int> </key> <value> <string>No</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>10</Order> <Name>FirstPatientRecruitedDate</Name> <FriendlyName>Date of First Patient Recruited</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>true</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>11</Order> <Name>ApplicationToPermissionDuration</Name> <FriendlyName>Duration between VRA and NHS Permission</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>12</Order> <Name>PermissionToFirstPatientDuration</Name> <FriendlyName>Duration between NHS Permission and First Patient</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>13</Order> <Name>ApplicationToFirstPatientDuration</Name> <FriendlyName>Duration between VRA and First Patient</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>14</Order> <Name>BenchmarkMetTypeId</Name> <FriendlyName>Benchmark Met</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>1500</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>1501</int> </key> <value> <string>Yes</string> </value> </item> <item> <key> <int>1502</int> </key> <value> <string>No</string> </value> </item> <item> <key> <int>1503</int> </key> <value> <string>Within 70 Days</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>15</Order> <Name>AddedByUserId</Name> <FriendlyName>AddedByUserId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>Site</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>138</int> </key> <value> <string>Unknown</string> </value> </item> <item> <key> <int>1</int> </key> <value> <string>CTP Submission Platform</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>16</Order> <Name>AmendedByUserId</Name> <FriendlyName>AmendedByUserId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>Site</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>138</int> </key> <value> <string>Unknown</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>17</Order> <Name>DateAdded</Name> <FriendlyName>DateAdded</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">2015-07-29T19:15:40.515375+01:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>18</Order> <Name>DateAmended</Name> <FriendlyName>DateAmended</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">2015-07-29T19:15:40.515375+01:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>19</Order> <Name>NotMetATypeId</Name> <FriendlyName>A - Permissions delayed/denied</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>20</Order> <Name>NotMetBTypeId</Name> <FriendlyName>B - Suspended by sponsor</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>21</Order> <Name>NotMetCTypeId</Name> <FriendlyName>C - Closed by sponsor</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>22</Order> <Name>NotMetDTypeId</Name> <FriendlyName>D - Sponsor Delays</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>23</Order> <Name>NotMetETypeId</Name> <FriendlyName>E - Staff availability issues</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>24</Order> <Name>NotMetFTypeId</Name> <FriendlyName>F - No patients seen</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>25</Order> <Name>NotMetGTypeId</Name> <FriendlyName>G - No patients consented</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>26</Order> <Name>NotMetHTypeId</Name> <FriendlyName>H - Contracting delays</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>27</Order> <Name>NotMetITypeId</Name> <FriendlyName>I - Rare diseases</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>28</Order> <Name>NotMetJTypeId</Name> <FriendlyName>J - Other</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>29</Order> <Name>NotMetKTypeId</Name> <FriendlyName>K - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>30</Order> <Name>NotMetLTypeId</Name> <FriendlyName>L - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>31</Order> <Name>NotMetMTypeId</Name> <FriendlyName>M - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>32</Order> <Name>NotMetNTypeId</Name> <FriendlyName>N - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>33</Order> <Name>NotMetOTypeId</Name> <FriendlyName>O - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>34</Order> <Name>Comments</Name> <FriendlyName>Comments</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>35</Order> <Name>ReasonForDelayTypeId</Name> <FriendlyName>Reasons for delay correspond to:</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2300</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2301</int> </key> <value> <string>NHS Provider</string> </value> </item> <item> <key> <int>2302</int> </key> <value> <string>Sponsor</string> </value> </item> <item> <key> <int>2303</int> </key> <value> <string>Both</string> </value> </item> <item> <key> <int>2304</int> </key> <value> <string>Neither</string> </value> </item> <item> <key> <int>-1</int> </key> <value> <string>Please Select...</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>false</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings>
Id |  | TrustId |  | SubmissionId |  | MetaSubmissionId |  | Research Ethics Committee Reference Number |  | Name of Trial |  | Date of Receipt of Valid Research Application |  | Date of NHS Permission |  | First Patient Recruited? |  | Date of First Patient Recruited |  | Duration between VRA and NHS Permission |  | Duration between NHS Permission and First Patient |  | Duration between VRA and First Patient |  | Benchmark Met |  | AddedByUserId |  | AmendedByUserId |  | DateAdded |  | DateAmended |  | A - Permissions delayed/denied |  | B - Suspended by sponsor |  | C - Closed by sponsor |  | D - Sponsor Delays |  | E - Staff availability issues |  | F - No patients seen |  | G - No patients consented |  | H - Contracting delays |  | I - Rare diseases |  | J - Other |  | K - Not Used |  | L - Not Used |  | M - Not Used |  | N - Not Used |  | O - Not Used |  | Comments |  | Reasons for delay correspond to:
Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value
blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 1401 | Yes | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 1501 | Yes | 138 | Unknown | 138 | Unknown | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | blank£%X_@# | blank£%X_@# | 2301 | NHS Provider
[16 empty] | 1402 | Yes - Date Unavailable | [8 empty] | 1502 | No | 1 | CTP Submission Platform | blank£%X_@# | blank£%X_@# |  |  |  |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  |  |  | 2302 | Sponsor
[16 empty] | 1403 | No | [8 empty] | 1503 | Within 70 Days | blank£%X_@# | blank£%X_@# | [6 empty] | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# |  |  | 2303 | Both
[16 empty] | blank£%X_@# | blank£%X_@# | [8 empty] | blank£%X_@# | blank£%X_@# | [40 empty] | 2304 | Neither
[68 empty] | -1 | Please Select...
[68 empty] | blank£%X_@# | blank£%X_@#

## Help
Spreadsheet Help