## DataSheet
Id | TrustId | SubmissionId | MetaSubmissionId | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | AddedByUserId | AmendedByUserId | DateAdded | DateAmended | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | K - Not Used | L - Not Used | M - Not Used | N - Not Used | O - Not Used | Comments | Reasons for delay correspond to: | Errors
70467 | 1066 | 3219 | 36 | 05/Q0508/95 | CHARMS (Childhood arthritis response to medication study) | 2015-01-05 | 2015-01-06 | No |  | 1 |  |  |  | CTP Submission Platform | Unknown | 2016-01-29 | 2016-01-29 | [15 empty] | Delay with Sponsor - site waiting for REC amendment to allow release of patient identifiable data. | Sponsor
70468 | 1066 | 3219 | 36 | 14/WM/0124 | UK full randomised controlled trial of arthroscopic surgery for hip impingement versus best conventional care (UK FASHIoN) | 2015-01-06 | 2015-01-07 | Yes | 2015-02-11 | 1 | 35 | 36 | Yes | CTP Submission Platform | Unknown | 2016-01-29 | 42398 | [16 empty] | Please Select...
70469 | 1066 | 3219 | 36 | 12/NW/0361 | A pragmatic randomised controlled trial comparing the effectiveness and cost effectiveness of levetiracetam and zonisamide versus standard treatments for epilepsy: A comparison of Standard and Antiepileptic Drugs (SANADII) | 2015-02-02 | 2015-02-04 | No |  | 2 |  |  |  | Unknown | Unknown | 2016-01-29 | 42398 | [5 empty] | Y |  |  | Y | [6 empty] | Rare patients at this Trust, thus study closed at this site at request of the PI and R&D office with the agreement of the Sponsor. | Neither
70470 | 1066 | 3219 | 36 | 14/SW/1166 | A multi-centered randomised trial to compare 1-stage with 2-stage revision surgery for prosthetic hip joint infection. | 2015-01-19 | 2015-02-18 | Yes | 2015-05-29 | 30 | 100 | 130 | No | Unknown | Unknown | 2016-01-29 | 42398 | [5 empty] | Y | [9 empty] | No Revision patients seen to date. Please note VRA received Monday 19th january not Sunday 18th January. | Neither
70471 | 1066 | 3219 | 36 | 14/WM/1063 | Platelet-rich plasma (PRP) versus Autologous blood versus placebo in the treatment of resistant tennis elbow | 2015-02-23 | 2015-02-24 | Yes | 2015-03-10 | 1 | 14 | 15 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [15 empty] | 1 patient consented, but not randomised yet - awaiting clinic date. Pt now received treatment. | NHS Provider
70472 | 1066 | 3219 | 36 | 15/NW/0005 | Medial Rotation Knee Randomised Controlled Trial All-polyethylene versus metal backed tibia | 2015-03-02 | 2015-03-09 | Yes | 2015-04-14 | 7 | 36 | 43 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [16 empty] | Neither
70473 | 1066 | 3219 | 36 | 08/H06041170 | A multicentre randomised double blind placebo controlled efficacy and safety trial if i.v. zolendronic acid twice yearly compared to placebo in osteoporotic children treated with glucocorticoids. | 2015-03-16 | 2015-03-18 | No |  | 2 |  |  |  | Unknown | Unknown | 2016-01-29 | 42398 | [9 empty] | Y | [5 empty] | Await SIV. Study to closed at this site band site to become a PIC and send eligible patient to another research site. | Sponsor
70474 | 1066 | 3219 | 36 | 14/NW/0339 | POPULAR | 2015-02-24 | 2015-02-26 | Yes | 2015-03-04 | 2 | 6 | 8 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [16 empty] | Please Select...
70475 | 1066 | 3219 | 36 | 14/EE/0204 | Hydrotherapy for DMD: a pilot feasibility randomised controlled trial in children | 2015-04-14 | 2015-04-28 | Yes | 2015-06-24 | 14 | 57 | 71 | No | Unknown | Unknown | 2016-01-29 | 42398 | [5 empty] | Y |  |  | Y | [6 empty] | Small number of eligible patients. | Neither
70476 | 1066 | 3219 | 36 | 15/WM/0078 | The SCOPIC trial ? Sciatica outcomes in primary care. Stratified care for patients with sciatica and suspected sciatica in primary care | 2015-06-26 | 2015-06-26 | Yes | 2015-07-17 | 0 | 21 | 21 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [16 empty] | Please Select...
70477 | 1066 | 3219 | 36 | 15/WM/0170 | Greater trochanteric pain syndrome: Does extracorporeal shock wave lithotripsy help? | 2015-06-18 | 2015-07-01 | Yes | 2015-07-28 | 13 | 27 | 40 | Yes | Unknown | Unknown | 2016-01-29 | 42398 |  |  |  |  | Y | [10 empty] | Delay due to staff availability over the summer holidays. | NHS Provider
70478 | 1066 | 3219 | 36 | 15/NW/0062 | Evaluation of an acellular osteochondral graft for cartilage lesions european post market study | 2015-08-05 | 2015-08-21 | Yes | 2015-10-19 | 16 | 59 | 75 | No | Unknown | Unknown | 2016-01-29 | 42398 | Y |  |  |  |  | Y |  |  |  | Y | [5 empty] | Patients meeting the eligibility criteria have been hard to find. 2 patients have been pre-screened, but not yet entered into the study. Delay to the start of the study due to MRI capacity at the Trust and the lack of support to source MRI capacity from another provider. First patient now recruited. | NHS Provider
70479 | 1066 | 3219 | 36 | 14/LO/2229 | Neuromuscular Rare Disease Translational Research in patients with Duchenne Muscular Dystrophy | 2015-08-27 | 2015-09-09 | Yes | 2015-10-20 | 13 | 41 | 54 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [8 empty] | Y | [7 empty] | Neither
70480 | 1066 | 3219 | 36 | 15/WM/0198 | Managing contracture and spasticity with standing frame vibration: Feasibility study using the ORLAU standing frame? | 2015-09-14 | 2015-09-22 | Yes | 2015-11-13 | 8 | 52 | 60 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [5 empty] | Y | [9 empty] | This is a pilot study for proof of concept and as such requires careful selection of the participants. | NHS Provider
70680 | 1066 | 3219 | 36 | 15/WM/0142 | New abduction orthosis for Ponseti treated patients. | 2015-06-01 | 2015-06-16 | Yes | 2015-07-30 | 15 | 44 | 59 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [16 empty] | Please Select...
70681 | 1066 | 3219 | 36 | 14/WS/1153 | A MULTICENTER STUDY TO ASSESS THE SAFETY AND PERFORMANCE OF SURGICLOT | 2015-05-20 | 2015-06-22 | Yes | 2015-07-20 | 33 | 28 | 61 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [16 empty] | Please Select...
70682 | 1066 | 3219 | 36 | 15/WM/0187 | Study of pre and post treatment nerve root tractography in the lumbar spine | 2015-06-10 | 2015-09-01 | Yes | 2015-12-07 | 83 | 97 | 180 | No | Unknown | Unknown | 2016-01-29 | 42398 | Y |  |  |  | Y | [10 empty] | MRI capacity issues in the Imaging Dept. and the disagreement between NHS waiting times and research targets, meant that there was no capacity for research studies. | NHS Provider
70683 | 1066 | 3219 | 36 | 15/LO/1253 | ACCEPT: Evaluation of methodology used in the assessment of acceptability of paediatric medicines: A mixed methods approach. | 2015-12-03 | 2015-12-16 | Yes | 2016-01-08 | 13 | 23 | 36 | Yes | Unknown | Unknown | 2016-01-29 | 42398 | [16 empty] | Please Select...
Upload Submission
Validate

## Hidden Data (hidden)
SpreadsheetOne - Hidden Data
******** PLEASE DO NOT CHANGE ANY OF THESE VALUES ********
| Hidden Data Key | Hidden Data Value |  | XML |  | Class
| Is First Open | FALSE |  | <?xml version="1.0" encoding="utf-16"?> <DataTableDataExportContainerOfPerformanceInitiationDetail xmlns:xsd="http://www.w3.org/2001/XMLSchema" xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance"> <DataTypeName>Exbos.Applications.NHSRBVP.Components.BusinessObjects.PerformanceInitiationDetail, Exbos.Applications.NHSRBVP.Components.BusinessObjects, Version=1.0.10.0, Culture=neutral, PublicKeyToken=null</DataTypeName> <Site Id="1" AddressId="-1" StatusId="51" TypeId="401" CultureId="1" AddedByUserId="1" AmendedByUserId="1" DateAdded="2013-06-15T22:56:16" DateAmended="2013-06-15T22:56:16"> <Name>CTP Submission Platform</Name> <Description/> </Site> </DataTableDataExportContainerOfPerformanceInitiationDetail> |  | PerformanceInitiationDetail
| Development Mode | FALSE
| Data Id | 3219
| User Id | -1
| Data Id | 40
<ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>1</Order> <Name>Id</Name> <FriendlyName>Id</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>2</Order> <Name>TrustId</Name> <FriendlyName>TrustId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">1066</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>3</Order> <Name>SubmissionId</Name> <FriendlyName>SubmissionId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">3219</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>4</Order> <Name>MetaSubmissionId</Name> <FriendlyName>MetaSubmissionId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">36</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>NotEmpty</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>5</Order> <Name>ReferenceNumber</Name> <FriendlyName>Research Ethics Committee Reference Number</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>NotEmpty</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>6</Order> <Name>TrialName</Name> <FriendlyName>Name of Trial</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>7</Order> <Name>ReceiptDate</Name> <FriendlyName>Date of Receipt of Valid Research Application</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>true</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>8</Order> <Name>PermissionDate</Name> <FriendlyName>Date of NHS Permission</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>9</Order> <Name>FirstPatientRecruitedTypeId</Name> <FriendlyName>First Patient Recruited?</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>1400</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>1401</int> </key> <value> <string>Yes</string> </value> </item> <item> <key> <int>1402</int> </key> <value> <string>Yes - Date Unavailable</string> </value> </item> <item> <key> <int>1403</int> </key> <value> <string>No</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Date</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>10</Order> <Name>FirstPatientRecruitedDate</Name> <FriendlyName>Date of First Patient Recruited</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">1753-01-01T12:00:00</DefaultValue> <UseCustomErrorValidator>true</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>11</Order> <Name>ApplicationToPermissionDuration</Name> <FriendlyName>Duration between VRA and NHS Permission</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>12</Order> <Name>PermissionToFirstPatientDuration</Name> <FriendlyName>Duration between NHS Permission and First Patient</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>Integer</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>true</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>13</Order> <Name>ApplicationToFirstPatientDuration</Name> <FriendlyName>Duration between VRA and First Patient</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-99999911</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>14</Order> <Name>BenchmarkMetTypeId</Name> <FriendlyName>Benchmark Met</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>1500</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>1501</int> </key> <value> <string>Yes</string> </value> </item> <item> <key> <int>1502</int> </key> <value> <string>No</string> </value> </item> <item> <key> <int>1503</int> </key> <value> <string>Within 70 Days</string> </value> </item> <item> <key> <int>-1</int> </key> <value> <string>Please Select...</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>true</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>true</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>15</Order> <Name>AddedByUserId</Name> <FriendlyName>AddedByUserId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>Site</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>1</int> </key> <value> <string>CTP Submission Platform</string> </value> </item> <item> <key> <int>138</int> </key> <value> <string>Unknown</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>16</Order> <Name>AmendedByUserId</Name> <FriendlyName>AmendedByUserId</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>Site</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>138</int> </key> <value> <string>Unknown</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>17</Order> <Name>DateAdded</Name> <FriendlyName>DateAdded</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">2016-01-29T11:14:10.2645+00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>DateTime</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>18</Order> <Name>DateAmended</Name> <FriendlyName>DateAmended</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:dateTime">2016-01-29T11:14:10.2645+00:00</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>19</Order> <Name>NotMetATypeId</Name> <FriendlyName>A - Permissions delayed/denied</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>20</Order> <Name>NotMetBTypeId</Name> <FriendlyName>B - Suspended by sponsor</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>21</Order> <Name>NotMetCTypeId</Name> <FriendlyName>C - Closed by sponsor</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>22</Order> <Name>NotMetDTypeId</Name> <FriendlyName>D - Sponsor Delays</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>23</Order> <Name>NotMetETypeId</Name> <FriendlyName>E - Staff availability issues</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>24</Order> <Name>NotMetFTypeId</Name> <FriendlyName>F - No patients seen</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>25</Order> <Name>NotMetGTypeId</Name> <FriendlyName>G - No patients consented</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>26</Order> <Name>NotMetHTypeId</Name> <FriendlyName>H - Contracting delays</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>27</Order> <Name>NotMetITypeId</Name> <FriendlyName>I - Rare diseases</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>28</Order> <Name>NotMetJTypeId</Name> <FriendlyName>J - Other</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>29</Order> <Name>NotMetKTypeId</Name> <FriendlyName>K - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>30</Order> <Name>NotMetLTypeId</Name> <FriendlyName>L - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>31</Order> <Name>NotMetMTypeId</Name> <FriendlyName>M - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>32</Order> <Name>NotMetNTypeId</Name> <FriendlyName>N - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>false</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>33</Order> <Name>NotMetOTypeId</Name> <FriendlyName>O - Not Used</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2200</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2201</int> </key> <value> <string>Y</string> </value> </item> <item> <key> <int>2202</int> </key> <value> <string> </string> </value> </item> </DataTypeCache> <IncludePleaseSelect>false</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">2202</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>String</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>34</Order> <Name>Comments</Name> <FriendlyName>Comments</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>-1</DataTypeId> <DataType>None</DataType> <MaxLength>-1</MaxLength> <DataTypeCache/> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>true</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:string"/> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings> |  | <ColumnSettings> <PropertyTypeString>Int32</PropertyTypeString> <WarningValidationRule>None</WarningValidationRule> <ErrorValidationRule>None</ErrorValidationRule> <Visible>true</Visible> <CanBeEmpty>false</CanBeEmpty> <DoNotAutoLoadCache>false</DoNotAutoLoadCache> <Order>35</Order> <Name>ReasonForDelayTypeId</Name> <FriendlyName>Reasons for delay correspond to:</FriendlyName> <UseTextArea>false</UseTextArea> <DataTypeId>2300</DataTypeId> <DataType>Type</DataType> <MaxLength>-1</MaxLength> <DataTypeCache> <item> <key> <int>2301</int> </key> <value> <string>NHS Provider</string> </value> </item> <item> <key> <int>2302</int> </key> <value> <string>Sponsor</string> </value> </item> <item> <key> <int>2303</int> </key> <value> <string>Both</string> </value> </item> <item> <key> <int>2304</int> </key> <value> <string>Neither</string> </value> </item> <item> <key> <int>-1</int> </key> <value> <string>Please Select...</string> </value> </item> </DataTypeCache> <IncludePleaseSelect>true</IncludePleaseSelect> <PleaseSelectIsError>false</PleaseSelectIsError> <ReadOnly>false</ReadOnly> <DefaultValue xmlns:xsi="http://www.w3.org/2001/XMLSchema-instance" xsi:type="xsd:int">-1</DefaultValue> <UseCustomErrorValidator>false</UseCustomErrorValidator> <UseCustomWarningValidator>false</UseCustomWarningValidator> <UseCustomValueCalulator>false</UseCustomValueCalulator> </ColumnSettings>
Id |  | TrustId |  | SubmissionId |  | MetaSubmissionId |  | Research Ethics Committee Reference Number |  | Name of Trial |  | Date of Receipt of Valid Research Application |  | Date of NHS Permission |  | First Patient Recruited? |  | Date of First Patient Recruited |  | Duration between VRA and NHS Permission |  | Duration between NHS Permission and First Patient |  | Duration between VRA and First Patient |  | Benchmark Met |  | AddedByUserId |  | AmendedByUserId |  | DateAdded |  | DateAmended |  | A - Permissions delayed/denied |  | B - Suspended by sponsor |  | C - Closed by sponsor |  | D - Sponsor Delays |  | E - Staff availability issues |  | F - No patients seen |  | G - No patients consented |  | H - Contracting delays |  | I - Rare diseases |  | J - Other |  | K - Not Used |  | L - Not Used |  | M - Not Used |  | N - Not Used |  | O - Not Used |  | Comments |  | Reasons for delay correspond to:
Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value | Id | Value
blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 1401 | Yes | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 1501 | Yes | 1 | CTP Submission Platform | 138 | Unknown | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | 2201 | Y | blank£%X_@# | blank£%X_@# | 2301 | NHS Provider
[16 empty] | 1402 | Yes - Date Unavailable | [8 empty] | 1502 | No | 138 | Unknown | blank£%X_@# | blank£%X_@# |  |  |  |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  | 2202 |  |  |  | 2302 | Sponsor
[16 empty] | 1403 | No | [8 empty] | 1503 | Within 70 Days | blank£%X_@# | blank£%X_@# | [6 empty] | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# | blank£%X_@# |  |  | 2303 | Both
[16 empty] | blank£%X_@# | blank£%X_@# | [8 empty] | -1 | Please Select... | [40 empty] | 2304 | Neither
[16 empty] | blank£%X_@# | blank£%X_@# | [8 empty] | blank£%X_@# | blank£%X_@# | [40 empty] | -1 | Please Select...
[68 empty] | blank£%X_@# | blank£%X_@#

## Help
Spreadsheet Help