## Sheet1
2016-17 Q3 Performance in Initiating
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
95361 | 14/LO/0807 | 148365 | NHS Permission | TARVA: To determine which of the 2 surgical procedures provide the better outcome for end stage OA in the 50-85 year age group. | 2016-01-19 | 2016-01-20 | Yes | 2016-03-29 | 1 | 69 | 70 | Yes | [5 empty] | Please Select... | [12 empty] | Please Select...
95362 | 14/NE/1176 | 161888 | NHS Permission | UK Frost- UK Frozen Shoulder Trial | 2016-02-02 | 2016-02-17 | Yes | 2016-04-05 | 15 | 48 | 63 | Yes | [5 empty] | Please Select... | [12 empty] | Please Select...
95363 | 15/EM/0153 | 146735 | NHS Permission | The Outcomes in Ankle Replacement Study (OARS): A study of patient reported outcomes following total anke replacement based on data from the National Joint Registry for England and Wales | 2016-02-11 | 2016-02-17 | Yes | 2016-03-16 | 6 | 28 | 34 | Yes | [5 empty] | Please Select... | [12 empty] | Please Select...
95364 | 15/WM/0101 | 173028 | NHS Permission | A prospective, non-comparative clinical investigation of a novel dellularised porcine xenograft (d CELL ACL Scaffold) for reconstruction of the Anterior Cruciate Ligament | 2016-02-16 | 2016-02-25 | No |  | 9 |  |  | No | [5 empty] | Please Select... |  | Y |  | Y |  |  | Y |  |  |  |  | Delay at site due to Imaging problems. No suitable patients seen to date. Study closed by sponsor with no recruitment at this site. | NHS Provider
95365 | 15/NW/0954 | 189188 | NHS Permission | Can shear wave elastography differentiate benign from malignant soft tissue tumours? | 2016-03-31 | 2016-04-26 | Yes | 2016-05-06 | 26 | 10 | 36 | Yes | [5 empty] | Please Select... | [11 empty] | Single site non-HRA process thus unable to complete all fields. | Please Select...
95366 | 16/YH/0177 | 200699 | NHS Permission | What are the predicting factors of kneeling after Total & Partial Knee Replacement? | 2016-04-18 | 2016-05-10 | Yes | 2016-05-13 | 22 | 3 | 25 | Yes | [5 empty] | Please Select... | [11 empty] | Single site non-HRA process thus unable to complete all fields. | Please Select...
95367 | 16/EM/0222 | 200401 | HRA Approval | The EFficacy of COntralateral muscle Rehabilitation exercise following anterior cruciate ligament reconstruction (EFCOR) |  |  | No |  |  |  |  | No | 2016-05-12 | 2016-05-12 | 2016-08-10 | 2016-05-12 | 2016-05-12 | Please Select... | 2017-01-30 |  |  |  | Y | Y | [5 empty] | Delays in starting study due to time between REC approval and HRA approval (17th June 2016 to 10th August 2016), plus delay on site / sponsor with employment contracts. Await date ready to start - research team in process of purchasing equipment etc. Study due to start 30/01/2017 - next available clinic date. | Both
95500 | 16/NW/0673 | 211391 | HRA Approval | Arm cycling in fascioscapulohumeral dystrophy (FSHD) patients: a feasibility study |  |  | No |  |  |  |  | No |  |  | 2016-11-09 | 2016-12-09 | 2016-12-09 | Please Select... | 2016-12-14 | [10 empty] | Single site study, unable to add all data required as not applicable. | Both
96018 | 16/EM/0301 | 206169 | HRA Approval | Kinetmatic Alignment compaRed to Mechanical Alignment techniques for total knee replacement surgery (KARMA) |  |  | No |  |  |  |  | No |  |  | 2016-09-01 | 2016-10-13 | 2016-10-13 | Please Select... | 2016-10-21 |  |  |  |  | Y | [5 empty] | Single site study, unable to add all data required as not applicable. Delay due to other clinical comitments by CI. | NHS Provider
96019 | 14/YH/0076 | 141623 | HRA Approval | The BALANCED Anaesthesia Study: A prospective, randomised clinical trial of two levels of anaesthetic depth on patient outcome after major surgery. |  |  | Yes | 2016-12-29 |  |  |  | No | 2016-07-13 | 2016-07-13 | 2016-07-25 | 2016-07-13 | 2016-07-13 | Please Select... | 2016-12-13 | [10 empty] | Delay to start due to SIV date | Sponsor