## Initiation
Submission Details
Status | Accepted
Open Date | 2015-01-01
Deadline Date | 2015-01-30
Date Submitted | 2015-02-06
Type | Performance in Initiating
NHS provider | The Robert Jones and Agnes Hunt Orthopaedic Hospital NHS Foundation Trust
Showing records 1 to 14 of 14.
Pages: 1
Id | Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
45111 | 14/WM/0043 | A Sprint National Anaesthesia Project (SNAP) to survey patient reported outcome after anaesthesia in UK hospitals | 2014-03-23 | 2014-05-06 | Yes | 2014-05-13 | 44 | 7 | 51 | Yes | [11 empty] | Please Select...
45112 | 13/YH/0371 | International Surgical Outcomes Study (ISOS) | 2014-05-13 | 2014-05-15 | Yes | 2014-05-19 | 2 | 4 | 6 | Yes | [11 empty] | Please Select...
45113 | 12-SC-0091 | Fracture Free study: A prospective cohort of patients presenting with a fragility fracture examining the predictors of re-fracture. | 2014-06-18 | 2014-06-20 | Yes | 2014-07-10 | 2 | 20 | 22 | Yes | [11 empty] | Please Select...
45114 | 12/NE/0293 | Prospective single arm multiconfiguration investigation to assess the functional performance of Attune primary total knee arthroplasty system. (10004 PRO Knee Assessment- Attune). | 2014-05-28 | 2014-07-02 | Yes | 2014-07-09 | 35 | 7 | 42 | Yes | [11 empty] | Please Select...
45115 | 14/SW/0072 | Understanding treatment of infection after joint replacement: a qualitative study (INFORM) | 2014-07-02 | 2014-07-02 | Yes | 2014-09-24 | 0 | 84 | 84 | No |  |  |  | Y |  | Y |  |  |  |  | Delayed to 05/08/2014 in receiving the "green light" from the Sponsor, followed by delay in finding suitable patients. | Both
45116 | 12/SC/0028 | Can Shoulder Arthroscopy Work- CSAW | 2014-07-10 | 2014-07-21 | Yes | 2014-10-14 | 11 | 85 | 96 | No | [5 empty] | Y |  |  |  |  | Delay due to type of patient required for study | Neither
45117 | 14/EM/1027 | Early v protected weight bearing post microfracture surgery | 2014-08-17 | 2014-09-08 | No |  | 22 |  |  | No | [9 empty] | Y | Delay due to amendment required to the protocol to enhance recruitment | NHS Provider
45118 | 13/NW/0663 | A Questionnaire for the Chronic Spinal Cord Injury Patient Population: 'Translational Research for Spinal Cord Injury (SCI): Current and Future Perspectives'. | 2014-07-31 | 2014-09-17 | No |  | 48 |  |  | No | [6 empty] | Y |  |  |  | Potential participants have been approached, but no participant conseted to date | Neither
45144 | 14/LO/0775 | An open non-comparitive clinical investigation of a novel decellularised porcine xenograft (dCell meniscus) for partial replacement of the meniscus. | 2014-09-23 | 2014-10-01 | No |  | 8 |  |  | No |  |  |  | Y | [6 empty] | Delay with Sponsor being able to supply surgery instruments. | Sponsor
45145 | 14/SC/1101 | Efficacy of a probiotic preparation (Yakult) containing a minimum of 6.5 x 10 to the power 9 Lactobacillus casei Shirota (LcS) compared to placebo for the prevention of AAD. | 2014-08-13 | 2014-10-22 | Yes | 2014-11-14 | 70 | 23 | 93 | No |  |  |  | Y |  |  |  | Y |  |  | Delay with Lead NHS site acting as Sponsor providing contract and written confirmation of funding. | Sponsor
45146 | 13/NW/0189 | Global prospective multicentre non-randomised controlled non-inferiortrial to evaluate symptom relief in patients with medical knee OA treated with the KineSpring implant for load reduction comapared to High tibial osteotomy (HTO). | 2014-09-23 | 2014-10-24 | Yes | 2014-11-19 | 31 | 26 | 57 | Yes | [11 empty] | Please Select...
45147 | 13/SC/0418 | An exploration of strategies to enhance physical activity (PA) in people with Rheumatoid Arthritis (RA) | 2014-11-04 | 2014-11-12 | Yes | 2015-01-06 | 8 | 55 | 63 | Yes | [11 empty] | Please Select...
45148 | 14/NW/0217 | What is the best way to fuse lumbar spine - anterior or posterior? | 2014-08-06 | 2014-12-01 | No |  | 117 |  |  | No | [9 empty] | Y | Delay in securing agreement with Support Service Dept. - Imaging for MRI | NHS Provider
46667 | 14/SC/1199 | Investigation of bone mineral content and body composition in men with coeliac disease | 2014-11-10 | 2014-11-17 | Yes | 2014-12-09 | 7 | 22 | 29 | Yes | [11 empty] | Please Select...
Showing records 1 to 14 of 14.
Pages: 1

## Delivery
Submission Details
Status | Accepted
Open Date | 2015-01-01
Deadline Date | 2015-01-30
Date Submitted | 2015-02-06
Type | Performance in Delivering
NHS provider | The Robert Jones and Agnes Hunt Orthopaedic Hospital NHS Foundation Trust
Showing records 1 to 6 of 6.
Pages: 1
Id | Research Ethics Committee Reference Number | Name of Trial | Target number of patients available | Target number of patients | Date Agreed to recruit target number of patients available | Date Agreed to recruit target number of patients | Trial Status | Target met within the agreed time | Comments
40261 | 14/LO/0775 | An open non-comparitive clinical investigation of a novel decellularised porcine xenograft (dCell meniscus) for partial replacement of the meniscus. | Available | 9 | Available | 2015-07-31 | Open | N/A | Delay to start of study due to Sponsor delay with instrumentation.
40262 | 14/SC/1101 | Efficacy of a probiotic preparation (Yakult) containing a minimum of 6.5 x 10 to the power 9 Lactobacillus casei Shirota (LcS) compared to placebo for the prevention of AAD. | Available | 100 | Available | 2017-03-31 | Open | N/A | First patient recruited within 70 days.
40263 | 13/NW/0189 | Global prospective multicentre non-randomised controlled non-inferiortrial to evaluate symptom relief in patients with medical knee OA treated with the KineSpring implant for load reduction comapared to High tibial osteotomy (HTO). | Available | 20 | No Date Agreed With Sponsor |  | Open | N/A | First patient recruited within 70 day target. Due to competitive recruitment, recruitment window not agreed.
42184 | 13/SC/0418 | An exploration of strategies to enhance physical activity (PA) in people with Rheumatoid Arthritis (RA) | Available | 50 | Available | 2015-02-28 | Open | N/A | First patient recruited within 70 days.
42185 | 14/NW/0217 | What is the best way to fuse lumbar spine - anterior or posterior? | Available | 100 | Available | 2015-12-31 | Open | N/A | Delay to recruitment due to unavailability of extra capacity within Imaging Dept.
42186 | 14/SC/1199 | Investigation of bone mineral content and body composition in men with coeliac disease | No Target Agreed With Sponsor |  | Available | 2015-04-30 | Open | N/A | Retrospective study of data previously collected, thus collecting consent to use this information. Some patients are deceased.
Showing records 1 to 6 of 6.