## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
136830 | 18/YH/0014 | 224065 | Articular pilon fracture trial (ACTIVE) External frame versus internal locking plate for articular pilon fracture fixation: a multi-centre randomised controlled trial | No |  | 96 |  |  | 2018-05-25 | 2018-05-25 | 2018-02-13 | 2018-07-04 | 2018-08-29 | Please Select... | 2018-10-19 | G - No patients consented |  | NHS Provider
136831 | 17/YH/0120 | 208838 | A pragmatic multi-centre randomised controlled non-inferiority, cost effectiveness trial comparing injections of collagenase into the cord to surgical correction in the treatment of moderate Dupuytren?s Contracture in adult patients. | No |  | 7 |  |  | 2018-06-15 | 2018-06-18 | 2017-05-25 | 2018-06-06 | 2018-06-25 | Please Select... | 2018-11-30 | A - Permissions delayed/denied | Delayed start at stie due to format of pharmacy labels required by sponsor unable to produce in required format at RJAH due to equipment limitations. Now resolved and due to be signed off imminently. | Both
136832 | 16/EM/0257 | 186079 | Stratified Primary Care for Musculoskeletal Patients: the STarT MSK Trial. [The patient facing name is: The TAPS study] | Yes | 2018-10-24 | 64 | 22 | 86 | 2018-07-30 | 2018-07-30 | 2016-08-19 | 2018-07-30 | 2018-10-02 | Please Select... | 2018-10-02 |  |  | Please Select...
136833 | 17/SC/0311 | 223283 | Patient Journey Following Lumbar Spinal Fusion | Yes | 2018-09-20 | 51 | 82 | 133 | 2018-05-10 | 2018-05-10 | 2017-07-28 | 2018-05-10 | 2018-06-30 | Please Select... | 2018-09-04 |  |  | Please Select...
136834 | 18/NW/0291 | 243678 | Spontaneous Healing of Articular Cartilage (SHARC) | No |  | 146 |  |  | 2018-06-19 | 2018-06-19 | 2018-07-02 | 2018-07-03 | 2018-11-12 | Please Select... | 2018-11-20 |  |  | Please Select...
136835 | 17/EM/0481 | 233652 | COMPACT version 1.0 | Yes | 2018-10-10 | 14 | 91 | 105 | 2018-05-25 | 2018-06-27 | 2018-06-27 | 2018-07-05 | 2018-07-11 | Please Select... | 2018-09-28 |  |  | Please Select...
136836 | HSRGC/2018/256/D | 238457 | Scaling Up Quality Improvement in Surgical Teams (QIST) | No |  | 131 |  |  | 2018-05-16 | 2018-07-04 | 2018-04-11 | 2018-10-31 | 2018-11-12 | Please Select... | 2018-11-12 |  |  | Please Select...
136837 | 13/LO/1748 | 122521 | Improving standards of care and translational research in spinal muscular atrophy | Yes | 2018-10-23 | 78 | 6 | 84 | 2017-11-29 | 2018-07-31 | 2018-05-25 | 2018-10-04 | 2018-10-17 | Please Select... | 2018-10-17 |  |  | Please Select...
136838 | 18/LO/0634 | 238717 | RECAP | No |  | 48 |  |  | 2018-08-22 | 2018-08-24 | 2018-07-02 | 2018-08-24 | 2018-10-11 | Please Select... | 2108-10-11 |  |  | Please Select...
136839 | 18/NE/0292 | 252024 | SIDEROS E | Yes | 2018-12-04 |  |  | 90 | 2018-09-05 | 2018-09-05 | 2018-11-15 | 2018-11-26 |  | Please Select... | 2018-11-28 |  |  | Please Select...
136840 | 18/WA/0254 | 218285 | Changes in Calf Properties following interventions for toe walking | No |  | 80 |  |  | 2018-09-07 | 2018-09-07 | 2018-09-05 | 2018-09-21 | 2018-11-26 | Please Select... | 2018-11-28 |  |  | Please Select...
136841 | 18/WA/0242 | 232678 | The RaCeR Study: Rehabilitation forllowing rotator cuff repair | No |  | 92 |  |  | 2018-10-08 | 2018-10-08 | 2018-09-06 | 2018-10-08 | 2019-01-08 | Please Select... | 2019-10-08 |  |  | Please Select...
136842 | 18/SW/0162 | 248769 | Single Use PICO NPWT post market safety and efficacy study | Yes | 2018-12-07 | 27 | 17 | 44 | 2018-10-24 | 2018-10-24 | 2018-07-26 | 2018-11-16 | 2018-11-20 | Please Select... | 2018-11-20 |  |  | Please Select...
136843 | 19/LO/0124 | 251237 | Expert Views on adult transition in young people with muscular dystrophy | Yes | 2019-03-20 | 12 | 37 | 49 | 2019-01-30 | 2019-01-30 | 2018-02-11 | 2019-02-11 | 2019-02-11 | Please Select... | 2019-03-07 |  |  | Please Select...
Showing records 1 to 14 of 14.
Pages: 1