## Sheet1
Performance in delivering Q1 2017/18 (April 2017 - June 2017)
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Target Number Of Patients Agreed? | Minimum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Maximum Number Of Patients Agreed (Enter Same In Both If Only One Number) | Target Date To Recruit Patients Agreed? | Date Agreed to recruit target number of patients | Total Number Of Patients Recruited At The Agreed Target Date | Date That The Trial Closed To Recruitment | Total Number Of Study Participants Recruited | Reason For Closure Of Trial | Comments
21193 | 14/LO/0775 | 151489 | dCell Meniscus (MUSC-3504) | Range Agreed | 2 | 9 | Not Available / Not Agreed |  |  | 2016-07-19 | 0 | Withdrawn By Sponsor | Study closed early by sponsor
21194 | 15/WM/0101 | 173028 | d CELL ACL Scaffold MUSC 4642 | Number Agreed | 10 | 10 | Not Available / Not Agreed |  |  | 2016-07-19 | 0 | Recruitment Finished | Study closed by sponsor as global recruitment target achieved
21195 | 10/H1208/20 | 46027 | The Finsbury Orthopaedics DeltaMotion Cup System | Number Agreed | 50 | 50 | Date Agreed | 2016-12-31 | 85 | 2016-12-31 | 85 | Recruitment Finished
21196 | 15/NW/0005 | 164614 | Medial Rotation Knee Randomised Controlled Trial All-polyethylene versus metal backed tibia | Number Agreed | 50 | 50 | Date Agreed | 2016-02-28 | 31 | 2017-01-03 | 53 | Recruitment Finished | Delay in recruitment due to Trust requirement to concentrate on waiting time initiatives, thus delay in new patients being operated on.
21197 | 15/NW/0062 | 168516 | Evaluation of an acellular osteochondral graft for cartilage lesions european post market study | Number Agreed | 5 | 5 | Not Available / Not Agreed |  |  | 2017-06-26 | 1 | Withdrawn By Sponsor | Recruitment closed early by sponsor