## Sheet1
Research Ethics Committee Reference Number | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
14/WM/0043 | A Sprint National Anaesthesia Project (SNAP) to survey patient reported outcome after anaesthesia in UK hospitals | 2014-03-23 | 2014-05-06 | Yes | 2014-05-13 | 44 | 7 | 51 | Yes
13/YH/0371 | International Surgical Outcomes Study (ISOS) | 2014-05-13 | 2014-05-15 | Yes | 2014-05-19 | 2 | 4 | 6 | Yes
12-SC-0091 | Fracture Free study: A prospective cohort of patients presenting with a fragility fracture examining the predictors of re-fracture. | 2014-06-18 | 2014-06-20 | Yes | 2014-07-10 | 2 | 20 | 22 | Yes
12/NE/0293 | Prospective single arm multiconfiguration investigation to assess the functional performance of Attune primary total knee arthroplasty system. (10004 PRO Knee Assessment- Attune). | 2014-05-28 | 2014-07-02 | Yes | 2014-07-09 | 35 | 7 | 42 | Yes
14/SW/0072 | Understanding treatment of infection after joint replacement: a qualitative study (INFORM) | 2014-07-02 | 2014-07-02 | Yes | 2014-09-24 | 0 | 84 | 84 | No |  |  |  | Y |  | Y |  |  |  |  | Delayed to 05/08/2014 in receiving the "green light" from the Sponsor, followed by delay in finding suitable patients. | Both
12/SC/0028 | Can Shoulder Arthroscopy Work- CSAW | 2014-07-10 | 2014-07-21 | Yes | 2014-10-14 | 11 | 85 | 96 | No | [5 empty] | Y |  |  |  |  | Delay due to type of patient required for study | Neither
14/EM/1027 | Early v protected weight bearing post microfracture surgery | 2014-08-17 | 2014-09-08 | Yes | 2015-02-09 | 22 | 154 | 176 | No | [9 empty] | Y | Delay due to amendment required to the protocol to enhance recruitment | NHS Provider
13/NW/0663 | A Questionnaire for the Chronic Spinal Cord Injury Patient Population: 'Translational Research for Spinal Cord Injury (SCI): Current and Future Perspectives'. | 2014-07-31 | 2014-09-17 | Yes | 2014-09-23 | 48 | 6 | 54 | Yes | [10 empty] | Potential participants have been approached, but no participant conseted to date. | Neither
14/LO/0775 | An open non-comparitive clinical investigation of a novel decellularised porcine xenograft (dCell meniscus) for partial replacement of the meniscus. | 2014-09-23 | 2014-10-01 | No |  | 8 | [6 empty] | Y | [5 empty] | Y | Delay with Sponsor being able to supply surgery instruments. Delay also due to Imaging Dept. capacity to prvide MRI scans for research v managing waiting times. | Both
14/SC/1101 | Efficacy of a probiotic preparation (Yakult) containing a minimum of 6.5 x 10 to the power 9 Lactobacillus casei Shirota (LcS) compared to placebo for the prevention of AAD. | 2014-08-13 | 2014-10-22 | Yes | 2014-11-14 | 70 | 23 | 93 | No |  |  |  | Y |  |  |  | Y |  |  | Delay with Lead NHS site acting as Sponsor providing contract and written confirmation of funding. | Sponsor
13/NW/0189 | Global prospective multicentre non-randomised controlled non-inferiortrial to evaluate symptom relief in patients with medical knee OA treated with the KineSpring implant for load reduction comapared to High tibial osteotomy (HTO). | 2014-09-23 | 2014-10-24 | Yes | 2014-11-19 | 31 | 26 | 57 | Yes | [11 empty] | Please Select...
13/SC/0418 | An exploration of strategies to enhance physical activity (PA) in people with Rheumatoid Arthritis (RA) | 2014-11-04 | 2014-11-12 | Yes | 2015-01-06 | 8 | 55 | 63 | Yes | [11 empty] | Please Select...
14/NW/0217 | What is the best way to fuse lumbar spine - anterior or posterior? | 2014-08-06 | 2014-12-01 | No |  | 117 | [12 empty] | Y | Delay in securing agreement with Support Service Dept. - Imaging for MRI, issue being waiting time targets v research. | NHS Provider
14/SC/1199 | Investigation of bone mineral content and body composition in men with coeliac disease | 2014-11-10 | 2014-11-17 | Yes | 2014-12-09 | 7 | 22 | 29 | Yes
05/Q0508/95 | CHARMS (Childhood arthritis response to medication study) | 2015-01-05 | 2015-01-06 | No |  | 1 | [8 empty] | Y | [5 empty] | Neither
14/WM/0124 | UK full randomised controlled trial of arthroscopic surgery for hip impingement versus best conventional care (UK FASHIoN) | 2015-01-06 | 2015-01-07 | Yes | 2015-02-11 | 1 | 35 | 36 | Yes
12/NW/0361 | A pragmatic randomised controlled trial comparing the effectiveness and cost effectiveness of levetiracetam and zonisamide versus standard treatments for epilepsy: A comparison of Standard and Antiepileptic Drugs (SANADII) | 2015-02-02 | 2015-02-04 | No |  | 2 | [13 empty] | Rare patients at this Trust
14/SW/1166 | A multi-centered randomised trial to compare 1-stage with 2-stage revision surgery for prosthetic hip joint infection. | 2015-01-18 | 2015-02-18 | No |  | 31 | [8 empty] | Y |  |  |  |  | No Revision patients seen to date | Neither
14/WM/1063 | Platelet-rich plasma (PRP) versus Autologous blood versus placebo in the treatment of resistant tennis elbow | 2015-02-23 | 2015-02-24 | No |  | 1 | [8 empty] | Y |  |  |  | Y | 1 patient consented, but not randomised yet - awaiting clinic date. | NHS Provider
15/NW/0005 | Medial Rotation Knee Randomised Controlled Trial All-polyethylene versus metal backed tibia | 2015-03-02 | 2015-03-09 | No |  | 7 | [8 empty] | Y | [5 empty] | Neither
n/a | Survey of Physiotherapist INtervention with PMR patients | 2015-03-04 | 2015-03-09 | No |  | 5 | [12 empty] | Y | This is a physiotherapist survey - no patient involvement. | Neither
08/HO604/170 | A multicentre randomised double blind placebo controlled efficacy and safety trial if i.v. zolendronic acid twice yearly compared to placebo in osteoporotic children treated with glucocorticoids. | 2015-03-16 | 2015-03-18 | No |  | 2 | [12 empty] | Y | Await SIV | Sponsor
14/NW/0339 | POPULAR | 2015-02-24 | 2015-02-26 | Yes | 2015-03-04 | 2 | 6 | 8 | Yes